## Sheet1
*Executive Sponsor - The person who can legitimize and enable the project/initiative
1. Show active, visible support of project/initiative; model appropriate behaviors to subordinates
2. Provide compelling justification for why project is happening and how it will succeed (5 Barriers to Buy-in)
3. Ensure that the project remains a priority; hold Advocates responsible for supporting project
4. Communicate a clear understanding of goals and objectives of the project/initiative
5. Provide sufficient resources for the team and project to be successful; remove roadblocks to change
at executive level
*Project Champion - The Executive Sponsor's point person for the project/initiative and director of the effort
1. Serve as liaison between Executive Sponsor, Advocates, and Project Manager
2. Ensure all participants understand their roles and responsibilities (Executive Sponsor, Project Manager,
Advocates)
3. Ensure Executive Sponsor has all information, materials, and other preparation to support the project
4. Ensure all participants possess or are developing necessary skills to carry out their responsibilities
5. Reinforce the roles and responsibilities of all participants
6. Engage the Executive Sponsor at appropriate roadblocks and decision points to keep project moving
forward
*Advocate - A high-level individual (other than the sponsor) who controls resources necessary to the initiative
1. Show active, visible support of project; model appropriate behaviors to subordinates and peers
2. Communicate a clear understanding of goals and objectives of the project/initiative
3. Hold staff responsible for supporting project/initiative
4. Provide sufficient resources for staff to support project; remove roadblocks at the staff level
5. Communicate ideas, recommendations, or concerns to Project Champion and/or Executive Sponsor
*Project Manager - The individual who plans, coordinates, and executes the project/initiative
1. Coordinate with Project Champion, stakeholders, and other participants
2. Define the scope, timeline, success indicators, and project plan in partnership with Project Champion
and stakeholders
3. Manage the project team by running meetings and making project assignments as appropriate
4. Identify, communicate, and ensure resolution of problems as they arise
5. Provide regular status reports and briefings to the Project Champion, partners, stakeholders, etc.
6. Create and maintain all supporting documentation related to the project
*Project Team Member/Support - The individuals who support the Project Manager in completing the work
1. Attend scheduled project meetings as appropriate
2. Complete work as assigned by Project Manager
NOTE: It is everyone's responsibility to raise questions, concerns, and problems in a timely fashion.
Sample Project Responsibility Chart
Library Bond Construction Project
| Name | Department/Company | Project Role
1 | Williams, Zachary | County Manager | Executive Sponsor
2 | Ricks, David | General Services Director | Project Champion
3 | Collins, Alfred | General Services, Asst Director | Project Manager
4 | Szabo, John | Library Director | Partner
5 | TBD | TBD | Project Advocate
6 | TBD | TBD | Project Support